Terms of Reference

Integrated Public Health Rapid Assessment (IPHRA)

SSD4459

20688

1

Table of Contents

1. Executive Summary	3

1.1 Tools and Methods	3

1.2 Research Timeline	3

1.3 Dissemination	3

2. Rationale	4

2.1 Background	4

2.2 Intended Impact	4

3. Goals and Objectives	5

3.1 Specific Objectives and Research Questions	5

4. Methodology	6

4.1 Methodology Overview	6

4.2 Population of Interest	6

4.3 Secondary Data Review	7

4.4 Key Definitions	8

4.5 Primary Data Collection	9

4.5.1 Household Surveys	9

4.5.2 Key Informant Interviews	11

4.6 Data Processing and Analysis	12

4.6.1 Household Survey Data	12

4.6.2 Key Informant and Observation Data	14

4.6.3 Integrated Analysis	14

4.7 Limitations	15

5. Key Ethical Considerations and Related Risks	17

6. Roles and Responsibilities	17

7. Data Analysis Plans (DAPs)	18

7.1 Household Tool DAP	18

7.2 Community Key Informant DAP	20

7.3 Market Vendor KII DAP	23

8. References	26

List of Figures

Right-click and update field to generate table of figures.

List of Tables

Right-click and update field to generate table of tables.

# 1. Executive Summary

| Country of intervention | Type of Emergency |  | Type of Crisis | Mandating Body/ Agency |  | IMPACT Project Code |
| --- | --- | --- | --- | --- | --- | --- |
|  | Natural Disaster |  | Complex | UNICEF |  | 98BSY |
| Geographic Coverage |  | Population(s) |  |  | Stratification |  |  |
| County urban center and rural areas. |  | 45000 |  |  | Host and IDPs |  |  |
| Rationale |  |  |  |  |  |  |  |
| Recent flash flooding has disrupted service availability and accessibility, as well as increased exposure to public health risks in the population. |  |  |  |  |  |  |  |

## 1.1 Tools and Methods

| Tool | Sampling.Method | Sample.Size |
| --- | --- | --- |
| tool_household_iphra_v2 | simple_random - rlc | 496 |
| tool_kii_community_iphra_v2 | Purposive / Random Walk | 600 |

## 1.2 Research Timeline

## 1.3 Dissemination

| Audience Type | Expected Output Type | Dissemination Strategy | Access | Visibility |
| --- | --- | --- | --- | --- |
| Cluster(s) |  |  |  |  |
| Donor(s) |  |  |  |  |
| Operational Actor(s) |  |  |  |  |
| Other(s) |  |  |  |  |

# 2. Rationale

Note

Reviewer Note: Please take time to complete sections 2.1 and 2.2 to clearly explain the context in which the assessment would be conducted, key information needs, and the intended impact of the assessment.

## 2.1 Background

- Briefly describe the context, i.e. the crisis within which the IPHRA is planned.

- Information gap and needs i.e. what is known so far about the severity of the public health situaiton and coverage of core public health interventions, what remains to be known and why

## 2.2 Intended Impact

- Who are the key actors/ what are the key decision-making processes and milestones this research aims to inform?

- What would be the impact of this research be on at least one of the following: (1) Bringing about positive change in the day-to-day lives of the population of interest (2) Improving understanding of the current situation to inform ongoing or planned humanitarian interventions (3) Improving understanding of the current situation to inform strategic decision-making processes, including funding allocations (4) Contributing towards system-wide change

# 3. Goals and Objectives

Goal: To assess the severity of the public health outcomes and identify initial public health priorities for response to mitigate excess morbidity, malnutrition, and mortality.

## 3.1 Specific Objectives and Research Questions

Table 1: Specific objectives and research questions Pillar; Sub.Pillar; Objective; Research.Question. Demographics; Demographics; To understand the sex and age composition of the target population; What is the demographic composition of the population?. HealthStatus; Mortality; To estimate the level of mortality in the target population; What is the severity of health needs in the population?. HealthStatus; To understand the level of health needs in the target population; What is the severity of health needs in the population?. NutritionStatus; NutritionStatus; To estimate the level of acute malnutrition in the population; What is the severity of nutrition needs in the population?. FoodConsumption; Quantity; To estimate the quantity of individual food consumption; What is the severity of food consumption gaps at the individual level in the population?. Diversity; To estimate the quality of individual food consumption; What is the severity of food consumption gaps at the individual level in the population?. ExposureDisease; Hygiene; To estimate the level and access to hygienic practices in the population; What is the risk of disease exposure and transmission?. IncomeCoping; Income; To understand the level and sources of household income in the target population; To what degree is income available at the household level?. CopingCapacity; To understand the types of coping strategies available and used used to access basic goods and services in the target population; What are the main coping strategies household use when they cannot meet their basic needs or access services?. LivingConditions; ProtectionElements; To understand the extent to which the target population has access to adequate shelter and items to protect against exposure to the environment; To what extent do households have the adequate shelter and other means to protect themselves from exposure to the weather and environment?. Markets; Availability; To assess the availability of food and non-food items within markets used by the target population; To what extent are key market items available in markets?. Accessibility; To understand the main barriers and issues related to market access for the target population (physical, financial, social); What are the main barriers for households to access markets?. Functionality; To understand the extent of market functionality in the target population; To what extent are markets functional?. WASHServices; Availability; To understand the level of availability of WASH services at the community level in the target population; To what extent are key WASH services available at the community level?. HealthServices; Accessibility; To understand the main access barriers related to health services for the target population (physical, financial, social); What are the main barriers to the community accessing health services?. Environment; Sanitation - Coverage; To estimate the coverage of sanitation facilities in the target population; To what extent does the population have access to adequate sanitation facilities?.

# 4. Methodology

The general research design for the Integrated Public Health Rapid Assessment (IPHRA) (1) will consist of a mixed-methods approach constituting three main methods: household surveys; Key Informant Interviews (KIIs); and observation checklists, each of these methods having core and supplemental specialized tools and information that can be collected.

## 4.1 Methodology Overview

The household survey component will consist of a two-stage approach sampling strategy with sites selected in the first stage using simple random sampling from a list of accessible sites and households selected in the second stage using random location cluster (RLC) method. In RLC sampling, GPS points will be randomly generated over a bounded area of selected sites and an equal number of GPS points will be generated per site. Data collection teams will collect household interviews at the closest three households at each GPS point. Sites will have equal probability of selection due to a lack of reliable population data. Either a single stratum will be identified representing the target population, or if comparison between multiple groups is necessary than multiple strata will be selected. Within each stratum, a minimum of six sites will be either randomly or purposefully selected for assessment. Results are intended to provide localized results which are not generalizable beyond the assessed population.

## 4.2 Population of Interest

The geographic coverage of the assessment includes: [Specify geographic coverage]. The total population consists of [Specify total population size] people with approximately [Specify total population size included in the survey if different from total population size] people included in the survey and approximately [Specify total population size excluded from the survey if different from total population size] people excluded from the survey.The population will be stratified into the following strata with the following total population per stratum: stratum 1: 4000, stratum 2: 4000.

## 4.3 Secondary Data Review

The main assessment design is based off guidance documents and tools for Integrated Public Health Rapid Assessment (IPHRA), available on the IMPACT Intranet (soon, link to intranet). Secondly, the IPHRA toolkit is designed to align with the Acute Needs Framework (ANF) utilized by IMPACT Initiatives in their Acute Needs Analysis workstreams (2). The intention of the Secondary Data Review step is to identify existing data sources for various ANF Pillars and Sub-Pillars, and to identify data gaps which will inform the design of the primary data collection component of the IPHRA. The below figure illustrates the ANF framework and how it maps against the planned primary data collection, as well as secondary data sources planned to be utilized for this assessment.

Figure: Acute Needs Framework (ANF) and Data Collection Mapping

Acute Needs Framework (ANF) and Data Collection Mapping

The below table cites relevant secondary data sources for each of the ANF Pillars and Sub-Pillars, as well as the purpose for which each data source will be utilized in the assessment.

Table 1. Secondary Data Sources

| Objective | Source | Purpose |
| --- | --- | --- |

## 4.4 Key Definitions

Within this population, specific indicators will target sub-populations. All eligible sub-populations within sampled households will be included in the survey. Sub-populations for indicators include:

- Household Definition: A group of people who ate from the same cooking and slept under the same roof the previous night

- Global Acute Malnutrition (GAM) by MUAC: is the prevalence of acute malnutrition, or wasting, among children 6-59 months of age, measured through oedema, or by measuring the middle-upper arm circumference (MUAC). For this assessment, all children 6-59 months in sampled households will be eligible.

- GAM among women of reproductive age (15-49 years): is acute malnutrition among women of reproductive age, measured through the middle-upper arm circumference (MUAC). Acute malnutrition is diagnosed if the MUAC is below 230 millimetres. For this assessment, all women between the ages of 15-49 in sampled households will be eligible for inclusion.

- Mortality Rate: An incidence rate of deaths, that includes all deaths regardless of cause, age, or sex. It is measured for a given population for a specified recall period. This should include deaths both in the community and facility-based deaths. During humanitarian emergencies it is usually reported as deaths per 10,000 per day but can also be reported as deaths per 1000 per month or per person-time. Crude Mortality Rade (CMR) and Crude Death Rate (CDR) are interchangeable. All persons in sampled households will be eligible for inclusion. For children under-5 years of age, the under-5 mortality rate (U5MR) will also be calculated. The U5MR is the incidence rate of deaths among children under 5 years of age per 10,000 per day. For this assessment, all children under 5 years of age in sampled households will be eligible for inclusion.

- Early Childhood Food Insecurity Experience Scale (ECFIES): is a measure of the prevalence of food insecurity among children under 5 years of age based on the Food Insecurity Experience Scale (FIES) adapted for early childhood. It is measured through a set of questions asked to the caregiver about their child’s experience with food insecurity in the past 30 days. For this assessment, all children 6-59 months in sampled households will be eligible for inclusion.

## 4.5 Primary Data Collection

### 4.5.1 Household Surveys

There are several core and supplemental indicators within the household tool of the IPHRA toolkit. For the objectives of thisthis assessment the following are planned:

| Pillar | Sub.Pillar | Indicator |
| --- | --- | --- |
| Demographics | Demographics | Sex Ratio |
|  | Demographics | Proportion of Children Under-5 Years of Age (%) |
|  | Demographics | Mean Age (years) (#) |
|  | Demographics | Proportion of Women of Reproductive Age in the Population (%) |
| HealthStatus | Mortality | Crude Mortality Rate (deaths per 10,000 per day) |
|  | HealthStatus | Proportion of population with health needs in the previous two weeks (%) |
| NutritionStatus | NutritionStatus | Global Acute Malnutrition by MUAC for Children 6-59 months (%) |
|  | NutritionStatus | Global Acute Malnutrition by MUAC for Pregnant and Lactating Women (%) |
| FoodConsumption | Quantity | Proportion of Children Under-2 by Early Childhood Food Insecurity Experience Scale (EC-FIESE) (%) |
|  | Diversity | Proportion of Children Under-2 by Early Childhood Food Insecurity Experience Scale (EC-FIESE) (%) |
|  | Quantity | Proportion of Children Under-2 by Main Food Groups Consumed the Previous Day (%) |
|  | Diversity | Proportion of Children Under-2 by Main Food Groups Consumed the Previous Day (%) |

#### 4.5.1.1 Sample Size Calculations

Note

Reviewer Note: Please add justifications to the sample size tables to explain why each parameter was selected for sampling.

The sample size for the survey for General was calculated using the parameters in the table below:

Table 2. Sample size calculation parameters for General

| Parameter | Population.B | Population.A | Justification |
| --- | --- | --- | --- |
| Indicator Name | General | General |  |
| Sampling Design | Simple Random | Simple Random |  |
| Estimated Prevalence (%) | 10% | 10% |  |
| Desired Precision | 5% | 5% |  |
| Estimated population size | 5,000 | 5,000 |  |
| Design Effect | 1 | 1 |  |
| Finite Population Correction (FPC) used? | No | No |  |
| Individuals to be Included | 974 | 974 |  |
| Average Household Size | 6 | 6 |  |
| % sub-population | 15% | 15% |  |
| Non-Response Rate | 5% | 5% |  |
| Households to be Included | 163 | 163 |  |

The sample size for the rate survey for Crude Death Rate was calculated using the parameters in the table below:

Table 3. Sample size calculation parameters for Crude Death Rate

| Parameter | Population.B | Population.A | Justification |
| --- | --- | --- | --- |
| Indicator Name |  |  |  |
| Sampling Design | Simple Random | Simple Random |  |
| Expected Rate | 0.5 | 0.5 |  |
| Rate Precision | 0.4 | 0.4 |  |
| Rate Period | 90 | 90 |  |
| Population size (overall) | 5,000 | 5,000 |  |
| Design Effect | 1 | 1 |  |
| Finite Population Correction (FPC) used? | No | No |  |
| Population to be Included | 1,334 people | 1,334 people |  |
| Person-Time to be Included | 120,060 person days | 120,060 person days |  |
| Average Household Size | 6 | 6 |  |
| % Non-Respondents | 10% | 10% |  |
| Households to be Included | 248 households | 248 households |  |

#### 4.5.1.2 Site Selection Methods

The assessment will be conducted across 2 strata, with a total of 200 sites selected for the assessment. Different site selection methods will be used for different stratum The sites will be selected using the following methods:Simple Random Sampling: A total of 200 sites will be selected for the assessment covering ** Population B . Due to a lack of reliable population data, these sites will be selected with simple random sampling with each site having an equal chance of selection. This method for site selection is only applicable when no population data is available, however teams must evaluate population size, find estimates at field level, or evaluate relative population size between sites for later analysis. The sample will be allocated across selected sites with 8 households planned per site and additional weighting applied during analysis to account for under- or over-sampling of population groups between sites. Simple Random Sampling:** A total of 200 sites will be selected for the assessment covering ** Population A **. Due to a lack of reliable population data, these sites will be selected with simple random sampling with each site having an equal chance of selection. This method for site selection is only applicable when no population data is available, however teams must evaluate population size, find estimates at field level, or evaluate relative population size between sites for later analysis. The sample will be allocated across selected sites with 8 households planned per site and additional weighting applied during analysis to account for under- or over-sampling of population groups between sites.

#### 4.5.1.3 Household Selection Methods

Within selected sites, households will be selected using Random Location Cluster (RLC) sampling. In RLC sampling, random GPS points are generated within the boundary of selected sites. The boundaries and GPS points can be either set beforehand using GIS software, or while in the field with tools like REACH GeoRand. At each generated GPS points, enumerators are to start exactly, or as close as possible, to that point and then select the three physically closest households for interview. The enumerators should interview the selected household and then either (a) take the GPS point of that household or (b) estimate the approximate meters from the initial GPS point to the household.

#### 4.5.1.4 Team Composition, Training and Planning

The exact composition of teams will depend on the number of tools being implemented. For household surveys, teams will consist of one field supervisor and 3 enumerators. Where possible, teams should incorporate a mix of male and female enumerators. For key informant and observational tools, dedicated enumerators separate from the household survey enumerators will be selected and trained to implement them. One enumerator should not implement more than one or two specific tools to ensure adequate time for use in the field and data quality.

Teams will receive a base three-day training prior to data collection covering purpose of the survey, good interview practices and ethical conduct during public health assessment, field sampling procedures, and review of the survey, key informant and observational tools, and a one-day for pilot and planning activities. It is recommended to divide the team for separate tool review sessions to efficiently make use of training time.

An additional session will be included for training on MUAC measurements as well as a half day of training for a MUAC standardization test.An additional session will be included for training on mortality data collection and basic psychosocial first aid skills for enumerators to recognize and appropriately respond to distress during the survey.

Field supervisors will have a key role in ensuring research quality during data collection. Key responsibilities will include:

- Providing daily feedback sessions to the data collection team

- Monitoring completion of assessment against planned targets

- Completing cluster control forms

- Ensuring proper household sampling techniques are applied

- Providing supportive supervision to enumerators

### 4.5.2 Key Informant Interviews

There are several core and supplemental key informant tools within the IPHRA toolkit, however for the purposes of this assessment the following key informant interviews are planned to assess these dimensions:

| Tool | Pillar | Sub.Pillar |
| --- | --- | --- |
| Community Leader and Community Member KII | HealthStatus | HealthStatus |
| Community Leader and Community Member KII | ExposureDisease | Hygiene |
| Community Leader and Community Member KII | IncomeCoping | Income |
| Community Leader and Community Member KII | IncomeCoping | CopingCapacity |
| Community Leader and Community Member KII | LivingConditions | ProtectionElements |
| Community Leader and Community Member KII | WASHServices | Availability |
| Community Leader and Community Member KII | HealthServices | Accessibility |
| Community Leader and Community Member KII | Environment | Sanitation - Coverage |
| Market Vendor KII | Markets | Availability |
| Market Vendor KII | Markets | Accessibility |
| Market Vendor KII | Markets | Functionality |

At least one community leaders and at least two community members (not formal leaders) should be selected from each sampled community or site for the Community Key Informant Tool. Community members can act as informants and are included to balance out perspectives that may be missed if only community leaders are interviewed. It is recommended that a mix of purposive and random selection is used for identifying respondents:

- Purposive Selection: Community leaders should be purposefully selected based on those who have formal or informal leadership roles in the community and can speak on behalf of community members, such as village chiefs, deputy cheifs, etc.

- Random Selection: Community members should be randomly selected from the community to ensure a diversity of perspectives are included. Community leaders SHOULD NOT select these individuals for the assessment team. The aim of this random selection isn’t to ensure any statistical representativeness, but to ensure we are accessing unbiased perspectives in the community. Assessment teams should use a simple random walk following the below procedure:

  - First, go to the approximate center of the assessment site.

  - Second, spin and toss a pen into the air to determine a direction.

  - Third, walk approximately 45 seconds in that direction depending on the size of the area. Choose the household immediately on your right and ask if they consent to an interview. If not, move to the household immediately to the right of that.

  - Fourth, return to the center of town, walk approximately 45 seconds in the opposite direction and select the household on the immediate right for a second community member interview.

  - Adapt as needed based on the size and shape of the location.

In the event of specific at-risk or difficult to identify groups within the population, it may be necessary to identify key informants through snowball sampling by asking local service providers for referrals. Consider this if there are specific groups that you want their views represented in the community key informant tools.

Market vendors should be selected by purposive selection methods based on their leadership positions in the market or as service providers. Wherever possible, market authorities ashould be informed and consulted before interviews are conducted with vendors. Teams may conduct two to three interviews per market to ensure a diverse perspective on market conditions and vendor experiences.

## 4.6 Data Processing and Analysis

Template data collection tools with Kobo have been adapted for this assessment. Both quantitative and qualitative data will be collected using KoboCollect on Android devices and uploaded to a Kobo server.

### 4.6.1 Household Survey Data

Household data will be collected using a contextualized IPHRA KoboCollect tool. Cleaning, indicator calculations, and analysis will be done using a pre-prepared IPHRA application using R version 4.6.1 (2026-06-24 ucrt).

The data processing and analysis will differ between stratum due to varying sampling strategies. The following approaches will be used for the designated stratum:The household analysis will be treated as a weighted cluster design across sites with groupings of households at each GPS point treated as the clusters in the analysis. Survey weights will be generated between sites to correct for under- or over-sampling between sites based on the best available population estimated the field teams were able to recover. If no adequate population data was available during the assessment, the final analysis will be unweighted. If population density is assessed to be very different within or across assessment sites, survey weights will be used for each random location cluster equivalent to the inverse of the population density of each cluster. This is intended to correct for any bias due to an uneven population density across the assessment area to make sure households have a more equal representation in the dataset. Population density is estimated based on the number of people in households within a random location cluster divided by the area of the circle formed by the locations of the three households and the GPS point of that random location cluster.

An additional set of weights will be generated between strata to account for under- or over-sampling of population groups. Each set of weights will be multiplied together at the household level to generate a single set of composite weights for aggregated analysis.

#### 4.6.1.1 Mid-Upper Arm Circumference (MUAC) Analysis

Global acute malnutrition by MUAC will be calculated by classifying all children with MUAC <125mm and/or presence of bilateral pitting edema as acutely malnourished. Severe acute malnutrition by MUAC will be calculated by classifying all children with MUAC <115mm and/or presence of bilateral pitting edema as severely acutely malnourished. The analysis of these indicators will be disaggregated by sex and age group (6-11 months, 12-23 months, 24-35 months, 36-47 months, and 48-59 months). Children with extreme MUAC measurements less than 80mm or greater than 200mm will be excluded from the analysis due to likelihood of measurement error.

Global acute malnutrition by MUAC-for-Age z-scores (MFAZ) will be calculated by classifying all children with MUAC-for-Age z-score <-2 and/or presence of bilateral pitting edema as acutely malnourished. Severe acute malnutrition by MUAC-for-Age z-scores will be calculated by classifying all children with MUAC-for-Age z-score <-3 and/or presence of bilateral pitting edema as severely acutely malnourished. The analysis of these indicators will be disaggregated by age group (6-11 months, 12-23 months, 24-35 months, 36-47 months, and 48-59 months). Children with extreme MFAZ less than -4 SD from the mean MFAZ of the sample or greater than 4 standard deviations from the mean MFAZ of the sample will be excluded from the analysis due to likelihood of measurement error.

The ratio of children 0-23 months of age to children 24-59 months of age in the sample will be evaluated to determine if additional age weighting is needed for analysis of the indicator Global or Severe Acute Malnutrition by MUAC. If strong differences are observed against an expected proportion of two-thirds children 24-59 months out of all under-5 year old children, then a set of weights will be applied if the child is 0-23 months or 24-59 months for this specific indicator. The age weights will be multiplied with any household level weights to generate a single set of composite weight for analysis.

The quality of MUAC results will be evaluated by reviewing several key paramaters including standard deviation of MUAC, standard deviation of MFAZ, digit preference scores, sex and age ratios, and other indicators of measurement quality. Enumerators identified to be strongly influencing the results with poor quality MUAC measurements may be excluded from analysis. Quality of enumerator work will be assessed continuously throughout the survey period.

Global acute malnutrition by MUAC for women of reproductive age (15-49 years) will be calculated by classifying all women with MUAC <210mm as acutely malnourished and all women with MUAC <190mm as severely acutely malnourished. Results will be disaggregated by pregnancy status (pregnant, breastfeeding a child 0-5 months of age, breastfeeding a child 6-23 months of age, non-pregnant/non-breastfeeding). Extreme MUAC measurements of less than 100mm or greater than 300mm will be excluded from the analysis due to likelihood of measurement error.

#### 4.6.1.2 Mortality Rate Analysis

Crude mortality rate (CMR) will be calculated by dividing the number of deaths in the recall period by the total person-time at risk during the recall period and multiplying by 10,000 to get a rate per 10,000 population per day. Under-5 mortality rate (U5MR) will be calculated by dividing the number of deaths among children under 5 years of age in the recall period by the total person-time at risk among children under 5 years of age during the recall period and multiplying by 10,000 to get a rate per 10,000 under-5 population per day. Person-time at risk will be calculated for each household based on the number of people living in the household at the time of the survey times the number of days from the start of the recall period to the interview date of the household. Person-time will be subtracted from each household equal to the number of reported births and in-migrants to the household times half the number of recall days, and person-time will be added to each household equivalent to the number of deaths and out-migrants from the household times half the number of recall days. Crude and under-5 mortality rates will be disaggregated by sex, respondent reported broad cause of death (non-trauma, trauma, other), location of death (current place of residence, during migration, and last place of residence).

The quality of mortality results will be evaluated by reviewing several key parameters including the sex and age ratios of the sample, the internal consistency of reported deaths to the household, distribution of deaths across teams and clusters, and other indicators of data quality. Enumerators identified to be strongly influencing the results with poor quality mortality data may be excluded from analysis. Quality of enumerator work will be assessed continuously throughout the survey period.

### 4.6.2 Key Informant and Observation Data

Community key informant interviews and community observation checklists will be qualitatively analysed using a data saturation grid, with the objectives of (a) triangulating the self-perceived needs of the population against quantitative data, and (b) attaining a better qualitative understanding of the nature of needs and barriers. The qualitative analysis uses a two-step process: Firstly, qualitative responses or observations are categorized as pertaining to one or more pillars or sub-pillars of the Acute Needs Framework to facilitate comparison of results across tools; and secondly a rapid coding is conducted to identify common themes and issues within pillars and sub-pillars. Responses will be compared across assessed sites. A standardized data saturation grid is used to facilitate this analysis.

### 4.6.3 Integrated Analysis

The IPHRA is a mixed methods approach that uses both quantitative and qualitative approaches to triangulate the severity of population needs and service gaps. In order to facilitate this, an integrated analysis is conducted to compare the responses across tools and assign an overall severity per ANA dimension. The objective of this exercise is to provide a holistic understanding and prioritization of different dimensions that may be threatening public health.

The integrated analysis is conducted in three steps.

- Assign Severity for Quantitative Household Results

- Assign Severity for Qualitative Key Informant and ObservationResults

- Assign an Overall Severity

In order to have a holistic understanding of the severity of public health needs and service gaps, it is suggested to include an integrated analysis table. This table will assign severity to one of the RoEM domains based on the evidence captured within the IPHRA assessment. The analyst can use the recommended thresholds in the standards tables located in the IPHRA Guidance document to help assign severity, however these are recommendations based on standards and if needed these thresholds may be contextualized at the country level.

Table 4. Example Integrated Analysis Table

| Category | Pillar | Sub-Pillar | Group 1 | Group 2 | Group 3 |
| --- | --- | --- | --- | --- | --- |
| Health Outcomes (Individual Level) | Population Mortality | NA | High | Medium | Low |
|  | Nutritional Status | NA | Medium | High | Medium |
|  | Health Needs | NA | Low | Medium | High |
| Immediate Drivers (Individual Level) | Food Consumption | Quantity | Medium | High | Medium |
|  |  | Quality | High | Medium | Low |
|  | Water Consumption | Quantity | Medium | Low | High |
|  |  | Quality | Low | Medium | Medium |
|  | Exposure to Disease | Reproductive Numbers | High | Medium | Low |
|  |  | Hygiene | Not assessed | Not assessed | Not assessed |
| Direct Contributing Factors (Household Level) | Household Food Security | HH Food Consumption | Medium | High | Low |
|  |  | Availability | High | Medium | Medium |
|  |  | Accessibility | High | Low | High |
|  |  | Utilization | Medium | Medium | High |
|  |  | Stability | Low | High | Medium |
|  | Household Water Security | HH Water Consumption | Medium | High | Low |
|  |  | Availability | High | Medium | Medium |
|  |  | Accessibility | Medium | Low | High |
|  |  | Utilization | Low | Medium | Medium |
|  |  | Stability | Not assessed | High | Low |
|  | HH Income and Coping | Income | Not assessed | Not assessed | Not assessed |
|  |  | Coping Capacity | Medium | Low | High |
|  |  | Assets | Low | Medium | Medium |
|  | Living Conditions | Protection from Elements | Medium | High | Low |
| Indirect Contributing Factors (Community Level) |  | Protection from Vectors | High | Medium | Medium |
|  |  | Crowdedness | Medium | Low | High |
|  | Livelihoods | Availability | Low | Medium | High |
|  |  | Accessibility | Medium | High | Medium |
|  | Markets | Availability | High | Medium | Low |
|  |  | Accessibility | Medium | High | Medium |
|  |  | Functionality | Low | Medium | High |
|  | WASH Services | Availability | Medium | Low | High |
|  |  | Accessibility | High | Medium | Medium |
|  |  | Quality | Medium | High | Low |
|  |  | Utilization | Low | Medium | Medium |
|  | Nutrition Services | Coverage | Not assessed | High | Low |
|  |  | Availability | Medium | Low | High |
|  |  | Accessibility | High | Medium | Medium |
|  |  | Quality | Medium | High | Low |
|  |  | Utilization | Low | Medium | Medium |
|  | Health Services | Coverage | High | Not assessed | Medium |
|  |  | Availability | Medium | High | Low |
|  |  | Accessibility | Low | Medium | High |

## 4.7 Limitations

The IPHRA methodology is intended to be a rapid assessment toolkit to provide an indication of the most key public health outcomes and service coverage indicators compared to other more robust methods. Given the suggested IPHRA methods, there are a few limitations to keep in mind:

- Not a Causal Analysis – The intent of the IPHRA methods is to understand the severity of public health needs and service gaps, however given this focus it may not fully explain the reasons or causes of the results. Some analysis and triangulation with qualitative components may given an indication, but it will likely be limited.

- Likely Not Reaching Saturation – For the qualitative components, sample sizes are likely not adequate to reach a full saturation of responses in the population. The intent of these is to provide some light-touch information to triangulate with household survey results.

- Accessibility – IPHRA is not a hard-to-reach methodology, and should only be applied to populations which the assessment team can physically access.

- The sampling approach is not a cluster design and is intended for a more localized population, therefore the results may not be generalizable and representative of the wider population.* The indicator Global Acute Malnutrition by MUAC is calculated based on the measurement of mid-upper arm circumference of children aged 6-59 months. This may not be a fully accurate representation of the nutritional status of the population, as it does not account for other factors or measures that may signify acute malnutrition such as weight for height comparisons.* The indicators Crude Mortality Rate and Under-5 Mortality Rate are calculated based on the number of deaths reported by households during the recall period. This may not be a fully accurate representation of the mortality rates in the population, as it relies on self-reported data and may be subject to recall bias or underreporting. Furthermore given this is a rapid assessment, the limited sample size may not be sufficient to provide very precise estimates when mortality rates are very high - particularly with under-5 mortality which should be interpreted with caution given the small sample size.

# 5. Key Ethical Considerations and Related Risks

Note

Reviewer Note: For any ethical consideration that is not met below, please specify any mitigation strategies and liaise with the Research Quality Unit (RQA).

The proposed research design meets / does not meet the following criteria:

Table 5. Ethical Considerations and Risks

| The proposed research design... | Yes/No | Details if no (including mitigation) |
| --- | --- | --- |
| ... Has been coordinated with relevant stakeholders to avoid unnecessary duplication of data collection efforts? |  |  |
| ... Respects respondents, their rights and dignity (specifically by: seeking informed consent, designing length of survey/discussion while being considerate of participants’ time, ensuring accurate reporting of information provided)? |  |  |
| ... Does not expose data collectors to any risks as a direct result of participation in data collection? |  |  |
| ... Does not expose respondents / their communities to any risks as a direct result of participation in data collection? |  |  |
| ... Does not involve collecting information on specific topics which may be stressful and/or re-traumatising for research participants (both respondents and data collectors)? |  |  |
| ... Does not involve data collection with minors i.e. anyone less than 18 years old? |  |  |
| ... Does not involve data collection with other vulnerable groups e.g. persons with disabilities, victims/survivors of protection incidents, etc.? |  |  |
| ... Follows IMPACT SOPs for management of personally identifiable information? |  |  |
| ... if an anthropometric component is included (MUAC data), will a standardization test be conducted or trained measurers from local nutrition partners be involved? |  |  |
| ... if a mortality component is included (crude mortality rates), will the assessment team receive any basic Psychosocial First Aid (PFA) [@pfa2018] training beforehand? |  |  |
| ... will assessment teams be aware of basic complaints and referral mechanisms in case needed during the course of the assessment? |  |  |

# 6. Roles and Responsibilities

Table 6. RACI Matrix

| Task Description | Responsible | Accountable | Consulted | Informed |
| --- | --- | --- | --- | --- |
| Research design | Assessment Officer | Research Manager | IMPACT STU | IMPACT RQA |
| Supervising data collection | Field Officer | Assessment Officer | Research Manager | Country Representative |
| Data processing (checking, cleaning) | Data Officer | Assessment Officer | IMPACT STU | IMPACT RQA |
| Data analysis | Data Officer | IMPACT RQA | IMPACT STU | Assessment Officer |
| Output production | Assessment Officer | IMPACT RQA | IMPACT STU | Assessment Officer |
| Dissemination | Assessment Officer | Research Manager | IMPACT Comms | IMPACT STU |
| Monitoring & Evaluation | Assessment Officer | Research Manager | Country Representative | IMPACT MEL |
| Lessons learned | Assessment Officer | IMPACT STU | Research Manager | IMPACT MEL |

# 7. Data Analysis Plans (DAPs)

## 7.1 Household Tool DAP

Table 7. Household Tool DAP

| Research Question | Indicator Name | Disaggregation | Question | Responses | Data Collection Level |
| --- | --- | --- | --- | --- | --- |
| What is the sex ratio in the population? | Sex Ratio | 5-year age bins | What is the sex of the individual? | Male Female | Individual |
| What is the average age of household members in the population? | Mean Age (years) (#) | Not applicable | What is the age of the individual? | Enter number | Individual |
|  |  |  | Do you know the day, month, and year **date of birth** of the individual? | Yes No | Individual |
| What is the proportion of children under-5 years of age in the population? | Proportion of Children Under-5 Years of Age (%) | Sex | What is the **date of birth** for the individual? | Date (DD/MM/YYYY) | Individual |
|  |  |  | If not exact date, can you estimate the **month-year of birth** for the individual? | Date (DD/MM/YYYY) | Individual |
| How many people are dying of any cause per 10,000 people per day during the recall period? | Crude Mortality Rate (deaths per 10,000 per day) | Sex, Reported Cause of Death, Reported Location of Death | Has anyone in your household passed away on or after the ${recall_event}? | Yes No | Individual |
|  |  |  | How many people in your household have DIED on or after the ${recall_event}? | Enter number | Individual |
|  |  |  | Sex: | Male Female | Individual |
|  |  |  | Age (years): | Enter number | Individual |
|  |  |  | Do you know the day, month, and year of birth of the dead person? | Yes No | Individual |
|  |  |  | What is the **date of birth** for the dead person? | Date (DD/MM/YYYY) | Individual |
|  |  |  | If exact date not known, please estimate at least the **month-year** of birth as best as possible using the local events calendar. | Date (DD/MM/YYYY) | Individual |
|  |  |  | Was the dead person present in the household on ${recall_event}? | Yes No | Individual |
|  |  |  | Do you know the dead person's **date of death**? | Yes No | Individual |
|  |  |  | **EXACT** date of death of the dead person? | Date (DD/MM/YYYY) | Individual |
|  |  |  | If exact date unknown, estimate the **month-year** of death of the dead person | Date (DD/MM/YYYY) | Individual |
|  |  |  | What was the main cause of death for the dead person? | Acute disease (malaria, fever, COVID-19, measles, cholera, diarrhoea, etc.) Chronic disease (cancer, heart disease, diabetes, stroke, etc.) Intentional violence Accident/trauma Post-partum (0-42 days) During pregnancy During delivery Other (specify) Don't know | Individual |
|  |  |  | If other, please specify how died? | Text response | Individual |
|  |  |  | Where did the dead person pass away? | Current location of residence Health facility at current location of residence During migraton or displacement At last place of residence Health facility at last place of residence Other (specify) Don't know | Individual |
|  |  |  | If other, please specify? | Text response | Individual |
|  |  |  | In your own words, can you provide any other details about the circumstances of the dead person's death? | Text response | Individual |
| What proportion of the population has had a health care need and needed to access health services in the past two weeks? | Proportion of population with health needs in the previous two weeks (%) | Sex, Age in Years | The following questions are for the ${health_ind_sex} with age in years: ${health_ind_age_years} | Text response | Individual |
|  |  |  | Has the individual had any illness or health problem in the last two weeks and needed to access health care? | Yes No Don't know | Individual |
|  |  |  | What symptoms did the individual have? | Fever Diarrhoea Cough Fast and difficulty breathing Eye infection or red eyes Skin infection Ear infection Rash with raised bumps on the head, neck Other (specify) Don't know Prefer not to answer | Individual |
|  |  |  | If other, please specify: | Text response | Individual |
| What is the prevalence of acute malnutrition amongst children 6-59 months of age in the population? | Global Acute Malnutrition by MUAC for Children 6-59 months (%) | Sex, Age in Months | The following questions are for the ${child_relationship} with age in months: ${child_age_months} and sex: ${child_sex} | Text response | Individual |
|  |  |  | Is the child present? | Yes No Yes, but the child is disabled / cannot be measured | Individual |
|  |  |  | Please take the MUAC of the child in CM: | Enter number | Individual |
|  |  |  | Does the child have bilateral oedema, that is swelling with pitting oedema in both feet? | Yes No | Individual |
|  |  |  | Please confirm with the team leader. Does the child have bilateral oedema? | Yes No | Individual |
|  |  |  | Please take a picture of the bilateral pitting oedema. Make sure to clearly include: - Both feet - Both impressions from the edema test |  | Individual |
| What are the food consumption patterns for children under two years of age in the population? | Proportion of Children Under-2 by Main Food Groups Consumed the Previous Day (%) |  | Was the child breastfed yesterday during the day or night? | Yes No Don't know | Individual |
|  |  |  | Which foods did the child consume in the last 24 hours? | Breast Milk Grains, roots, tubers and plantains Pulses (beans, peas, lentils), nuts and seeds Dairy products (milk, infant formula, yogurt, cheese) Flesh foods (meat, fish, poultry, organ meats) Eggs vitamin-A rich fruits and vegetables Other fruits and vegetables (non- Vitamin A) Don't know Other (specify) | Individual |
|  |  |  | If other, please specify: | Text response | Individual |
| How severe is food deprivation for children under two years of age in the population? | Proportion of Children Under-2 by Early Childhood Food Insecurity Experience Scale (EC-FIESE) (%) |  | Now I would like to ask you some questions about your experiences in feeding solid or semi-solid food to [NAME OF CHILD IN ID01]. During the last 7 days (week), was there a time when: | Text response | Individual |
|  |  |  | You (the parent or caregiver) were worried that the child would not have enough food to eat because of insufficient money or other resources? | Yes No Don't know Decline to answer | Individual |
|  |  |  | Still thinking about the last 7 days (week), was there a time when when the child was unable to eat nutritious and healthy foods because of insufficient money or other resources? | Yes No Don't know Decline to answer | Individual |
|  |  |  | Was there a time when your child ate fewer kinds of food because of insufficient money or other resources? | Yes No Don't know Decline to answer | Individual |
|  |  |  | Was there a time when your child skipped one or more meals in the day because of insufficient money or other resources? | Yes No Don't know Decline to answer | Individual |
|  |  |  | Still thinking about the last 7 days (week), was there a time when your child eat less food than you (the parent or caregiver) thought the child should because of insufficient money or other resources? | Yes No Don't know Decline to answer | Individual |
|  |  |  | Was there a time when your household ran out of food for the child because of insufficient money or other resources? | Yes No Don't know Decline to answer | Individual |
|  |  |  | Was there a time when your child was hungry but did not eat food because of insufficient money or other resources? | Yes No Don't know Decline to answer | Individual |
|  |  |  | Was there a time when your child did not eat food for a whole day because of insufficient money or other resources? | Yes No Don't know Decline to answer | Individual |
| What is the proportion of pregnant and lactating women with children under 6 months in the population? | Proportion of Women of Reproductive Age in the Population (%) | Not applicable | What is the status of the women individual in question? | None Currently pregnant Breasfeeding child under 6 month Breasfeeding child between 6 and 23 month | Individual |
| What is the prevalence of acute malnutrition amongst pregnant and lactating women in the population? | Global Acute Malnutrition by MUAC for Pregnant and Lactating Women (%) | Pregnancy and Lactation Status | Is the woman present? | Yes No | Individual |
|  |  |  | What is the MUAC for the woman in CM? | Enter number | Individual |

## 7.2 Community Key Informant DAP

Table 8. Community Key Informant DAP

| Research Question | Indicator Name | Disaggregation | Question | Responses | Data Collection Level |
| --- | --- | --- | --- | --- | --- |
| What are the most serious problems in the community as reported by community informants? | Proportion of community informants reporting a serious problem with water (%) | Key Informant Type | Q2.1 (Water) Does the community have a serious problem because you do not have enough water that is safe for drinking or cooking? | No serious problem Serious problem Do not know/Not Applicable/Decline to answer | Key Informant |
|  |  |  | Please describe the problem? Who has the problem? | Text response | Key Informant |
|  |  |  | What are the main barriers preventing the community from accessing enough safe drinking or cooking water? | Text response | Key Informant |
|  | Proportion of community informants reporting a serious problem with suitable living spaces (%) |  | Q2.3 (Place to Live In) Do people in the community have a serious problem because they do not have a suitable place to live in? | No serious problem Serious problem Do not know/Not Applicable/Decline to answer | Key Informant |
|  |  |  | Please describe the problem? Who has the problem? | Text response | Key Informant |
|  |  |  | What are the main barriers preventing the community from having a suitable place to live? | Text response | Key Informant |
|  | Proportion of community informants reporting a serious problem with sanitation (%) |  | Q2.4 (Toilets) Do people in the community have a serious problem because they do not have easy and safe access to a clean toilet? | No serious problem Serious problem Do not know/Not Applicable/Decline to answer | Key Informant |
|  |  |  | Please describe the problem? Who has the problem? | Text response | Key Informant |
|  |  |  | What are the main barriers preventing the community from having a suitable toilet? | Text response | Key Informant |
|  | Proportion of community informants reporting a serious problem being able to keep clean and hygienic (%) |  | Q2.5 (Keeping Clean) For men: Do people have a serious problem because in your community it is difficult for people to keep clean? For example, because people do not have enough soap, water or a suitable place to wash. For women: Do people have a serious problem because in your community it is difficult to keep clean? For example, because people do not have enough soap, sanitary materials, water or a suitable place to wash | No serious problem Serious problem Do not know/Not Applicable/Decline to answer | Household |
|  |  |  | Please describe the problem? Who has the problem? | Text response | Household |
|  |  |  | What are the main barriers preventing the community from being able to keep clean? | Text response | Household |
|  | Proportion of community informants reporting a serious problem with lack of clothing and bedding (%) |  | Q2.6 (Clothes, Shoes, Blankets) Do people in the community have a serious problem because they do not have enough, or good enough, clothes, shoes, bedding or blankets? | No serious problem Serious problem Do not know/Not Applicable/Decline to answer | Key Informant |
|  |  |  | Please describe the problem? Who has the problem? | Text response | Key Informant |
|  |  |  | What are the main barriers preventing the community from having enough, or good enough clothes, shoes, bedding or blankets? | Text response | Key Informant |
|  | Proportion of community informants reporting a serious problem due to lack of income, money or resources to live |  | Q2.7 (Income or Livelihoods) Do people have a serious problem because they do not have enough income, money or resources to live? | No serious problem Serious problem Do not know/Not Applicable/Decline to answer | Key Informant |
|  |  |  | Please describe the problem? Who has the problem? | Text response | Key Informant |
|  |  |  | What are the main barriers preventing people in the community from having enough income, money or resources to live? | Text response | Key Informant |
|  | Proportion of community informants reporting a serious problem with physical health in the community (%) |  | Q2.8 (Physical Health) Do people have a serious problem with their physical health? For example, because you have a physical illness, injury or disability. | No serious problem Serious problem Do not know/Not Applicable/Decline to answer | Key Informant |
|  |  |  | Please describe the problem? Who has the problem? | Text response | Key Informant |
|  |  |  | What are the causes of peoples’ issues with their physical health? | Text response | Key Informant |
|  | Proportion of community informants reporting a serious problem with not being able to get adequate health care (%) |  | Q2.9 (Health care) For men: Do men have a serious problem because they are not able to get adequate health care for themselves? For example, treatment or medicines. For women: Do they have a serious problem because they are not able to get adequate health care for themselves? For example, treatment or medicines, or health care during pregnancy or childbirth. | No serious problem Serious problem Do not know/Not Applicable/Decline to answer | Key Informant |
|  |  |  | Please describe the problem? Who has the problem? | Text response | Key Informant |
|  |  |  | What are the main barriers preventing people in the community getting adequate health care for themselves? | Text response | Key Informant |
|  | Proportion of community informants reporting a serious problem with inadequate aid (%) |  | Q2.11 (The way aid is delivered) Do you have a serious problem because of inadequate aid? For example, because you do not have fair access to the aid that is available, or because aid agencies are working on their own without involvement from people in your community? | No serious problem Serious problem Do not know/Not Applicable/Decline to answer | Key Informant |
|  |  |  | Please describe the problem? Who has the problem? | Text response | Key Informant |
|  |  |  | What are the main barriers preventing people in the community from having enough income, money or resources to live? | Text response | Key Informant |
|  | Proportion of community informants reporting a serious problem with feeling very distressed (%) |  | Q3.1 (Distress) Do people in the community have serious problems because they feel very distressed? For example, very upset, sad, worried, scared, or angry? | No serious problem Serious problem Do not know/Not Applicable/Decline to answer | Key Informant |
|  |  |  | If yes, please describe the problem? Who has this problem? | Text response | Key Informant |
|  |  |  | What are the causes of this distress for people? | Text response | Key Informant |
|  | Proportion of community informants reporting a serious problem with mental illness (%) |  | Q3.13 (Mental illness in your community) Is there a serious problem in your community because people have a mental illness? | No serious problem Serious problem Do not know/Not Applicable/Decline to answer | Key Informant |
|  |  |  | If yes, please describe the problem? Who has this problem? | Text response | Key Informant |
|  |  |  | What are the main reasons for this problem in the community? | Text response | Key Informant |

## 7.3 Market Vendor KII DAP

Table 9. Market Vendor KII DAP

| Research Question | Indicator Name | Disaggregation | Question | Responses | Data Collection Level |
| --- | --- | --- | --- | --- | --- |
| What are the main barriers to accessing markets in the population? | Qualitative report of physical access barriers to markets | Not applicable | Over the last X days/months, have some problems prevented any customers or traders from physically traveling to, working at, or shopping at this marketplace? | No issues with physical access to the marketplace Curfew or movement restrictions Ongoing/active fighting in the area Inadequate facilities make it difficult for businesses to operate Hazardous, damaged, or unsafe buildings in the marketplace Hazards or damage on roads leading to the marketplace Limited transportation options/lack of transportation Vendors are difficult to access for people with disabilities or mobility issues Marketplace is too far from the people who need it Marketplace only operates at limited times Customers do not feel safe around some people in the marketplace Don't know Prefer not to answer Other, please specify: | Vendor |
|  |  |  | Please describe other | Text response | Vendor |
|  | Qualitative report of social access barriers to markets |  | Over the last X days/months, have any groups of people sometimes avoided coming to this marketplace due to discrimination, exclusion, or feeling unwelcome? | Yes No Don't know | Vendor |
|  |  |  | If yes, can you explain how? | Text response | Vendor |
| What is the condition and functionality of markets in the population? | Qualitative report of damage to markets |  | Over the last X days/months, has the marketplace been damaged or affected? | Yes No Don't know | Vendor |
|  |  |  | If yes, please expand on what has been damaged: probe the infrastructure, storage capacity, and supply routes: | Text response | Vendor |
| What are the main barriers to accessing markets in the population? | Qualitative report of payment modality issues |  | Over the last X days/months, have you accepted any of the following payment types from your customers? | Cash (local currency) Cash (foreign currencies) Mobile money Credit/debit cards Money transfers Cheques Vouchers Informal credit (customers can buy now and pay later) Barter (customers can pay for goods with other goods) Prefer not to answer Other (please specify): | Vendor |
|  |  |  | Please explain the reason some payment types are not accepted? | Text response | Vendor |
| How available are common food items in markets used by the population? | Qualitative report of food item availability in the market |  | How would you describe the current availability of each of the following items in this market? | Text response | Vendor |
|  |  |  | Item 1 | Widely available Limited availability (only sold in small quantities or by a small number of traders) Completely unavailable Don't know Prefer not to answer Other, please specify: | Vendor |
|  |  |  | Item 2 | Widely available Limited availability (only sold in small quantities or by a small number of traders) Completely unavailable Don't know Prefer not to answer Other, please specify: | Vendor |
|  |  |  | Item 3 | Widely available Limited availability (only sold in small quantities or by a small number of traders) Completely unavailable Don't know Prefer not to answer Other, please specify: | Vendor |
|  |  |  | Item 4 | Widely available Limited availability (only sold in small quantities or by a small number of traders) Completely unavailable Don't know Prefer not to answer Other, please specify: | Vendor |
|  |  |  | Item 5 | Widely available Limited availability (only sold in small quantities or by a small number of traders) Completely unavailable Don't know Prefer not to answer Other, please specify: | Vendor |
| What are the main barriers to purchasing power in the population? | Qualitative report of item price changes |  | In the last [recall period], how has the price of each of the following items changed? | Text response | Vendor |
|  |  |  | Item 1 | No change Increased significantly Increased Slightly Decreased slightly Decreased significantly Don't know Prefer not to answer Other, please specify: | Vendor |
|  |  |  | Item 2 | No change Increased significantly Increased Slightly Decreased slightly Decreased significantly Don't know Prefer not to answer Other, please specify: | Vendor |
|  |  |  | Item 3 | No change Increased significantly Increased Slightly Decreased slightly Decreased significantly Don't know Prefer not to answer Other, please specify: | Vendor |
|  |  |  | Item 4 | No change Increased significantly Increased Slightly Decreased slightly Decreased significantly Don't know Prefer not to answer Other, please specify: | Vendor |
|  |  |  | Item 5 | No change Increased significantly Increased Slightly Decreased slightly Decreased significantly Don't know Prefer not to answer Other, please specify: | Vendor |
|  |  |  | If prices have changed, would you like to add more information to explain why? | Text response | Vendor |
| How available are common food items in markets used by the population? | Qualitative report of food item availability in the market |  | For how many days, not including today, do you estimate your stock of the following items will last under current conditions? | Text response | Vendor |
|  |  |  | Item 1 | Enter number | Vendor |
|  |  |  | Item 2 | Enter number | Vendor |
|  |  |  | Item 3 | Enter number | Vendor |
|  |  |  | Item 4 | Enter number | Vendor |
|  |  |  | Item 5 | Enter number | Vendor |
| How will market activity change in the coming period for markets serving the population? | Qualitative report of forecasted changes in market activity |  | Do you foresee any challenges or positive changes in the next X weeks/months to market activities? | Yes No Don't know | Vendor |
|  |  |  | If yes, please provide some details | Text response | Vendor |
|  |  |  | Any other closing remarks by the health care staff? | Text response | Vendor |

# 8. References

1. 	IMPACT Initiatives. Integrated public health rapid assessment (IPHRA) guidelines. Geneva, Switzerland: IMPACT Initiatives; 2026.

2. 	IMPACT Initiatives. The acute needs framework. Geneva, Switzerland: IMPACT Initiatives; 2026.